## Slide 1
NOTCH × BULLET
Project Kickoff Plan
Standing up Notch's first on-premise AI deployment in insurance
CUSTOMER Bullet (carrier + investor) FIRST CHANNEL WhatsApp V0
TIMELINE 1 Nov 2025 → end Q1 2026 MODEL On-prem · binary-only · self-hosted LLM

## Slide 2
01
PURPOSE
Why this engagement carries outsized weight
Proves the on-premise model
Binary-only, pull-based deployment is exactly what regulated industries demand. Get it right here, and it becomes the template.
First large US enterprise
A working reference in a Fortune-scale regulated buyer is the credential that opens the US enterprise market.
A reusable playbook
Insurance-specific work - compliance, guardrails, data sensitivity - is built once and inherited by the next regulated customer.
The customer is also an investor
Execution here is visible to the people funding Notch's next round. Delivery is a commercial and an investor signal at once.
NOTCH TARGET
90%
average automation
~50%
CS headcount reduction
200%
ROI within a year
Notch × Bullet
02

## Slide 3
02
CONTEXT
What Bullet asked for
On-premise deployment
Three environments (Dev / Staging / Production) on Bullet's own cloud. Notch never gets push access.
Multi-channel
Voice, WhatsApp, mobile App, and Website - the App is Bullet's stated 2026 priority.
Nine core features
IVR replacement, FAQ, OTP, data integration, guardrails, Glassix, scraping, deeplinks, prompt safety.
Aggressive timeline
Kickoff 1 Nov 2025, App targeted for the end-of-Q1-2026 deadline. Five months, on-prem, from scratch.
Notch × Bullet
03

## Slide 4
03
STRATEGY
Two projects, not one
Different people, different risks, different reasons to fail. They run in parallel and meet at exactly one handoff.
DEVOPS PROJECT
Workshops + binary pipeline
Dev → Staging → Production
Per-channel connectivity
PRODUCT PROJECT
Build flows on Notch platform
Mock-first, then real integration
Validated binaries
∥
The single convergence point Validated binary, pulled into Bullet's environment through the DevOps pipeline
Notch × Bullet
04

## Slide 5
04
SEQUENCING
One channel at a time, deliberately
1
WhatsApp
Pilot
Has a Glassix human fallback - the only safe place to find failure modes.
›
2
Mobile App
Priority
Bullet's 2026 goal. Reuses the proven core rather than discovering it.
›
3
Voice
Q2
Adds the hard part - real-time speech - once text is stable.
›
4
Website
Q2
Lowest marginal value, cheapest once the core is fully proven.
The reframe: WhatsApp-first is not a detour from the App deadline - it is the first recoverable increment of the exact core the App depends on.
Notch × Bullet
05

## Slide 6
05
ROADMAP
MVP committed, the rest sequenced
Nov
Dec
Jan
Feb
Mar
Apr
May
Q1 2026 deadline
Q4 2025
Q2 2026
WA V0
Dec
WA V1
Jan
WA V2
Feb
App
Mar
Voice
Apr
Web
May
COMMITTED · by end Q1 2026
WA V0 (Dec) · WA V1 (Jan) · WA V2 (Feb) · Mobile App (Mar)
V0-V2: WhatsApp pilot through complete. App - Bullet's priority - lands just inside the deadline.
SEQUENCED · into Q2 2026
Voice (Apr) · Web (May)
Hyper Care follows each go-live immediately. Optimization starts once a channel is stable. We protect the must-haves rather than force all five into five months.
Notch × Bullet
06

## Slide 7
06
MVP & DOD
Start small, go live fast
All four flows (A, B, C, D) are live in V0. The only change in V1 is Flow B coverage: one intent in V0, all remaining intents in V1.
V0 - PILOT · ALL FOUR FLOWS
✓
Flow A - Routing & Handoff - IVR + Glassix fallback
✓
Flow B - ONE intent only - proves pipeline, first containment
✓
Flow C - OTP + identity - customer identified from day one
✓
Flow D - Safety & Compliance baseline - always on
V1 - WHATSAPP FULL
= V0 unchanged + Flow B expanded (all remaining top intents). This is the only difference.
V2 - WHATSAPP COMPLETE
Full KB: all intents, not just top-N
Hardening: adversarial + prompt injection
Scraping: Bullet's web content auto-indexed
SUCCESS METRICS
Containment
% resolved E2E (calibrate target at kickoff)
Handoff quality
% handed off with context
Compliance
guardrail pass rate - zero PII tolerance
Notch × Bullet
07

## Slide 8
07
DELIVERY
Discover, mock, build, integrate
Almost everything we don't know is Bullet-specific. The expensive, access-dependent step is deliberately last.
1
1
Discover
Receive Swagger + API comprehension Q&A with Bullet's engineers.
→
2
2
Mock
Build accurate mocks from understood contracts. A deliverable in itself.
→
3
3
Build
Flows built on Notch's platform - no Bullet network needed yet.
→
4
4
Integrate
Swap mocks for real APIs once the logic is already mature.
Why mock-first is the whole game. Everything buildable without Bullet is built against mocks - fast and parallel. Bullet's access timeline becomes a constraint on the last mile, not a blocker on the whole build.
Notch × Bullet
08

## Slide 9
08
RESOURCES
Who we need on both sides
NOTCH TEAM
Project Manager delivery lead, dependency tracker, external sync
Implementation Manager business relationship, scope decisions (advisory)
Product requirements, backlog, acceptance criteria
DevOps / Infra Engineer owns the on-prem foundation
2 × Platform Developers the core build capacity
AI / Prompt Engineer agents, guardrails, tuning
QA / Test Engineer owns the testing funnel
BULLET TEAM · the critical path
Owner single coordination point - the must-have
DevOps / Cloud Engineer provisions envs, access, GPU
API / Backend owners Swagger + comprehension Q&A
Security / Compliance lead scanning, pentest, prod access
QA top intents, UAT, AI response correctness
Notch × Bullet
09

## Slide 10
09
QUALITY & ROLLOUT
Six gates, then Hyper Care
Every channel passes the same funnel, ordered by cost of failure - then a post-launch tail.
1
Stage testing
›
2
Bullet UAT
›
3
Pentest + load
›
4
Prod validation
›
5
PVT
›
6
Go-live
›
7
Hyper Care
›
8
Optimization
Hyper Care
Starts immediately after go-live - part of the delivery sequence, not deferred. 2-3 intensive weeks: elevated monitoring, a dedicated responder, a fast incident loop - before the channel is treated as steady-state.
Optimization
Starts once Hyper Care is complete and the channel is stable. Tuning prompts and guardrails against real conversations, expanding intent coverage. Starts after all preceding phases - unless Bullet's priorities direct otherwise.
Notch × Bullet
10

## Slide 11
10
RISKS
Scored, not just listed
Each risk is typed and scored on a 5×5 matrix (impact × probability), ranked by score.
2
3
1
5
4
IMPACT →
PROBABILITY →
1
Production access refused
Compliance
16 · Critical
2
Containment below target
Product
15 · High
3
Resource contention
Resourcing
12 · High
4
Binary fails security scan
Technical
8 · Medium
5
Tooling ownership unresolved
Commercial
4 · Low
Dependencies (what Bullet owes us) are tracked separately - they become risks only when a due date is missed.
Notch × Bullet
11

## Slide 12
11
KICKOFF
The kickoff meeting
AGENDA
Strategy & sequencing
Timeline & scope vs the Q1 2026 deadline
The deployment model
Lock the critical decisions
Access & discovery sign-off
First four weeks & owners
CRITICAL DECISIONS
Scope vs deadline (all 5 channels, or App?)
Build/buy boundary & vendors
Subscription ownership (recommend Bullet)
Production access model
KEY QUESTIONS, BY PRIORITY
P0 · BLOCKING
•
Is the Q1 2026 deadline immovable - all 5 channels or just App?
•
LLM self-hosted - does any data leave?
•
APIs documented (Swagger) and reachable?
•
Named Bullet Owner (single coordination point)?
•
Security scanning toolchain?
P1 · HIGH
•
Which 3rd-party tools does Bullet already run?
•
Per tool - who owns the subscription?
•
Top intents / volumes for the MVP?
•
GPU capacity for the self-hosted LLM?
P2 · BEFORE PHASE
•
Swagger / API docs for Policy & Claims endpoints?
•
Pentest owner & vendor?
•
PVT feasible per channel?
Notch × Bullet
12

## Slide 13
WHAT WINNING LOOKS LIKE
Live fast, recoverable, reusable
WhatsApp live fast and safely — the MVP recoverable behind a Glassix safety net
The App live on its priority timeline — by the end-of-Q1-2026 deadline
An architecture proven reusable — the next regulated customer inherits it, integration layer swapped not rebuilt
NEXT Send the pre-requisites this week · lock the critical decisions at kickoff · start the build on day one.